## DF01.01
Defect Id | DF01.01
Summary | When Clicked on the second museum (Royal Saudi Airforce Museum) , the location is not correct
Severity | Medium
Detected By | Hisham
Detected On | 2020-06-14
Status | Closed
Priority | Medium
Linked Test Case | TC01.05
Linked Requirement | RQ01
Root Cause | The museum location data was wrong in the database
Screenshot (.gif file) | https://res.cloudinary.com/dfrj1nea2/image/upload/v1592206900/Defects/Royal_AirForce_Museum_eb19wh.gif

## DF01.02
Defect Id | DF01.02
Summary | When Clicked on the fifth museum (King Salman Science Oasis) , the location is not correct
Severity | Medium
Detected By | Hisham
Detected On | 2020-06-14
Status | Closed
Priority | Medium
Linked Test Case | TC01.08
Linked Requirement | RQ01
Root Cause | The museum location data was wrong in the database
Screenshot (.gif file) | https://res.cloudinary.com/dfrj1nea2/image/upload/v1592206899/Defects/King_Salman_Oasis_Museum_iufkox.gif

## DF02.01
Defect Id | DF02.01
Summary | When Clicked on the fourth mosque (Princess Latifa Bint Sultan Bin Abdulaziz Grand Mosque) , the location is not correct
Severity | Medium
Detected By | Hisham
Detected On | 2020-06-14
Status | Closed
Priority | Medium
Linked Test Case | TC02.06
Linked Requirement | RQ02
Root Cause | The mosque location data was wrong in the database
Screenshot (.gif file) | https://res.cloudinary.com/dfrj1nea2/image/upload/v1592206898/Defects/Princess_Latifa_Mosque_pc6cge.gif

## DF03.01
Defect Id | DF03.01
Summary | When Clicked on the first mall (AL Nakheel Mall) , the location is not correct
Severity | Medium
Detected By | Hisham
Detected On | 2020-06-14
Status | Closed
Priority | Medium
Linked Test Case | TC03.03
Linked Requirement | RQ03
Root Cause | The mall location data was wrong in the database
Screenshot (.gif file) | https://res.cloudinary.com/dfrj1nea2/image/upload/v1592206900/Defects/Al_Nakheel_Mall_bil8me.gif